## routes
route | sub-route | Allowed to | Functionality | FPR | Status | Status updated on | Remarks | Endpoint | Test suite
/user | /login | all users | log in user and return JWT token | Jasdeep | current task | 2024-09-21 | to check option of cookies and logout | /api/user/login | user-login.test.js
| /register | public | register a new user to course |  | to be updated | 2024-09-17 | current version allows admin to register any user | /api/user/register
| /add | admin | add admin user | Jasdeep | done | 2024-09-20 | admin or super admin can create a new admin | /api/user/add | user-add.test.js
|  | Admin | add faculty | Jasdeep | done | 2024-09-21 | admin or super admin can create a new faculty (dependencies: valid departmentId and subjectId - to be tested) | /api/user/add | user-add.test.js
| /get | Admin or self | find the user by id | Jasdeep | to be updated | 2024-09-17
| /update | Admin or self | update user based on the role passed in data | Jasdeep | to be updated | 2024-09-17
| /delete | admin | delete the user from database
/subject | /add | Admin |  | Murtaza
| /find |  |  | Murtaza
| /update |  |  | Murtaza
| /delete | Admin |  | Murtaza
/department | /add | Admin |  | Ashish
| /find |  |  | Ashish
| /update |  |  | Ashish
| /delete | Admin
/course

## tasks
completed on | Team member | task | remarks
2024-09-17 | Jasdeep | tested login route with new endpoint | tested with jest and supertest. Test suit: test/user-login.test.js
2024-09-18 | Jasdeep | finalize student schema - merged student and applicant | Student schema will handle candidature to completion for a student. Additional schemas such as Application and Grade added for additional details.
2024-09-18 | Jasdeep | creation of super admin and middleware updation | If super admin does not exist, it gets created the first time the server starts. Middleware created to allow multiple route access.
2024-09-20 | Jasdeep | Wrote and tested /api/user/add route to add admin user | Tested with jest and supertest. api doc to be created.
2024-09-21 | Jasdeep | Wrote and tested /api/user/add route to add faculty | stand alone testing done. Yet to perform integration with department and subject models.

## weekly target
Date | Team member | Task | Expected completion | Completed on | Remarks
2024-09-18 | Jasdeep | add admin user and login for all users | 2024-09-25