## routes
route | sub-route | Allowed to | Functionality | FPR | Status | Status updated on | Remarks | Endpoint
/user | /login | all users | log in user and return JWT token | Jasdeep | changes required | 2024-09-18 | login will now return data according to polymorphic model | /api/user/login
| /register | public | registration for course |  | to be updated | 2024-09-17 | current version allows admin to register any user | /api/user/register
| /add | admin | add admin user | Jasdeep | current task | 2024-09-18 | creating route and controller for adding user | /api/user/add
|  | Admin | add faculty
| /find | Admin or self | find the user by id | Jasdeep | to be updated | 2024-09-17
| /update | Admin or self | update user based on the role passed in data | Jasdeep | to be updated | 2024-09-17
| /delete | admin | delete the user from database
/subject | /add | Admin |  | Murtaza
| /find |  |  | Murtaza
| /update |  |  | Murtaza
| /delete | Admin |  | Murtaza
/department | /add | Admin |  | Ashish
| /find |  |  | Ashish
| /update |  |  | Ashish
| /delete | Admin
/course

## tasks
date | Team member | task | completed on | remarks
2024-09-18 | Jasdeep | fully functional login route | 2024-09-17 | tested with jest and supertest. Test suit: test/user-login.test.js
2024-09-19 | Jasdeep | finalize student schema - merging student and applicant | 2024-09-18 | Student schema will handle canditature to completion for a student. Additional schemas such as Application and Grade added for additional details.
2024-09-19 | Jasdeep | creation of super admin and middleware updation

## weekly target
Created on | Team member | Task | Expected completion | Completed on | Remarks
2024-09-18 | Jasdeep | add admin user and login for all users | 2024-09-25