## routes
route | sub-route | Allowed to | Functionality | FPR | Status | Status updated on | Remarks
/user | /login | all users | log in user and return JWT token | Jasdeep | to be updated | 2024-09-17 | to change the main route to /api
| /register | public | register for the course | Jasdeep | to be updated | 2024-09-17
| /add | admin | add student/faculty based on the role passed in data
| /find | Admin or self | find the user by id | Jasdeep | to be updated | 2024-09-17
| /update | Admin or self | update user based on the role passed in data | Jasdeep | to be updated | 2024-09-17
| /delete | admin | delete the user from database
/subject | /add | Admin |  | Murtaza
| /find |  |  | Murtaza
| /update |  |  | Murtaza
| /delete | Admin |  | Murtaza
/department | /add | Admin |  | Ashish
| /find |  |  | Ashish
| /update |  |  | Ashish
| /delete | Admin
/course

## tasks
date | Team member | task | status | remarks
2024-09-18 | Jasdeep | fully functional login route